## 47 Processes By Knowledge Areas
Knowledge Area/Process Group | Initiating (2) | Planning (24) | Execute (8) | Monitor & Control (11) | Closing (2)
Integration (6) | Develop Project Charter | Develop Project Management Plan | Direct And Manage Project Work | Monitor and Control Project Work Perform Integrated Change Control | Close Project or Phase
Scope (6) |  | Plan Scope Management Collect Requirements Define Scope Create WBS |  | Validate Scope Control Scope
Time (7) |  | Plan Schedule Management Define Activities Sequence Activities Estimate Activities Resources Estimate Activity Durations Develop Schedule |  | Control Schedule
Cost (4) |  | Plan Cost Management Estimate Costs Determine Budget |  | Control Cost
Quality (3) |  | Plan Quality Management | Perform Quality Assurance | Control Quality
HR (4) |  | Plan HR Management | Acquire Project Team Develop Project Team Manage Project Team
Communications (3) |  | Plan Communications Management | Manage Communications | Control Communications
Risk (6) |  | Plan Risk Management Identify Risks Perform Qualitative Risk Analysis Perform Quantitative Risk Analysis Plan Risk Response |  | Control Risks
Procurement (4) |  | Plan Procurement Management | Conduct Procurements | Control Procurements | Close Procurements
Stakeholder (4) | Identify Stakeholders | Plan Stakeholder Management | Manage Stakeholder Engagement | Control Stakeholder Engagement

## ITTO Patterns
Initiating | Planning | Executing | Monitor & Controlling | Closing
| Every Plan takes the Project Management Plan | Every Process takes its own Management Plan | Every Process takes the Project Management Plan
Besides Perform Integrated Change Control, ALL processes output a Change Request
Besides Integration, ALL processes output Work Performance Information
Besides Integration, ALL processes Input Work Performance Data
Start looking at Knowledge Area+Process Group Patterns
See if Develop Schedule and Budget Process ITTOs are just the sum of all the ITTOs for the sub processes
See if the TTs for each MC Process matches their planning TTs